## Days Worked
Date | Day of Week | Project | Confidence | Focus / Task | Details | Evidence Source
2026-07-31 | Friday | Aqua Automation Factory | Approx. | Project kickoff - Agent 1 & Agent 2 built | Initial scaffolding: Agent 1 (.bds/XML/JSON parsers, doc template, splitter) and Agent 2 (prompt builder, CSV writer) source files created. | File timestamps
2026-08-05 | Wednesday | Aqua Automation Factory | Approx. | Agent 1 - real client .bds handling | Built the Baramundi-aware .bds digest extractor and schema-tolerant XML/JSON/text loader against the real client-supplied Install.bds. | File timestamps
2026-08-10 | Monday | Self-Healing Tests (Ellavait) | User-reported | Self-healing test engine built (rule-based, no AI) | Playwright + TypeScript engine that automatically fixes broken/flaky automated tests: handles broken locators (element changed) and flaky timing (test ran too early). Built sample tests plus deliberately broken/flaky tests to prove it works, and a "heal" command that fixes and re-verifies a failed test. Results: broken tests 0%->100% passing, flaky tests 33-83%->100% passing, stable tests stayed 100% with zero false alarms. Next: connect to the real Ellavait tests, add more element types (dropdowns, inputs), later a "click to heal" button and optional AI layer. | User-reported (separate project folder)
2026-08-12 | Wednesday | Aqua Automation Factory | Approx. | Agents 3, 4, 5 built + first real PR | Built Script Adaptation (Agent 3), Automation Review (Agent 4), and Execution & Self-Healing (Agent 5). Created the automation_target demo repo and merged the first real GitHub PR (#1). | File timestamps + git log
2026-08-13 | Thursday | Aqua Automation Factory | Approx. | Agent 3 continued | Added a second script-adaptation requirement (exact success message assertion). | File timestamps
2026-08-14 | Friday | Aqua Automation Factory | Approx. | Orchestration logic for Agents 1, 2, 4, 5 + self-heal | Built self_healer.py, doc_generator.py, test_generator.py, reviewer.py, adapter.py. Pull request #4 merged. | File timestamps + git log
2026-08-18 | Tuesday | Aqua Automation Factory | Approx. | Generalization testing - added a 7-Zip job | Built a second, structurally different Baramundi job (7-Zip) to prove the pipeline isn't overfit to one job type. Pull request #5 merged. | File timestamps + git log
2026-08-19 | Wednesday | Aqua Automation Factory | Approx. | Auto-triggering built | File-watching inbox (jobs/requirements) plus a scheduled regression cycle, so the pipeline can trigger itself instead of needing manual CLI runs. | File timestamps
2026-08-20 | Thursday | Aqua Automation Factory | Approx. | Multi-provider LLM support + durable audit trail + real Allure integration | Rewrote llm_client.py in all 5 agents to support Anthropic / OpenAI / Azure OpenAI / claude_cli. Rewrote events.py for a SQLite-based durable audit trail. Wired in real Allure test reporting. | File timestamps + git log
2026-08-21 | Friday | Aqua Automation Factory | High | Repo cleanup + grew test suite + fixed an Allure reporting bug | Merged/closed stale pull requests, deleted stale branches. Split both test scripts from 1 monolithic test each into 5 focused test cases (2 -> 10 total). Found and fixed a bug where the Allure report only showed the most-recently-run suite instead of both combined. | git log (automation_target)
2026-08-24 | Monday | Aqua Automation Factory | High | Unit tests for the agents' own code | Added 74 unit tests across all 5 agents covering parsing, CSV/report generation, git-command building, allow-list checks, and self-heal patching - no API key or real git calls needed. | File timestamps + conversation log
2026-08-25 | Tuesday | Aqua Automation Factory | High | Requirement -> test -> PR traceability report | Built a report tying each requirement to its GitHub pull request (live status) and current pass/fail result. Wired into Agent 5 so it self-refreshes every run. | File timestamps + conversation log
2026-08-26 | Wednesday | Aqua Automation Factory | High | Made the dashboard a persistent service | Set up a systemd --user service with auto-restart; verified it survives a killed process and survives logout (lingering enabled). | File timestamps + conversation log
2026-08-27 | Thursday | Aqua Automation Factory | High | Automatic Slack / webhook alerts | Built alerts for run failures, self-heal kicking in, and the approval gate waiting on a decision - verified end-to-end with a real local mock Slack receiver. | File timestamps + conversation log
2026-08-31 | Monday | Aqua Automation Factory | High | VM-deployment readiness pass | Fixed a real gap (.env files were created but never actually loaded), pinned all dependency versions, built a preflight health-check script plus a dashboard /health endpoint, and wrote an ops runbook. | File timestamps + conversation log

## Summary
Days Worked - Summary
Total distinct days with recorded work: | 15
Date range: | 2026-07-31 to 2026-08-31 (32 calendar days)
Projects covered: | Aqua Automation Factory, Self-Healing Tests (Ellavait)
High-confidence days (explicit daily task + file/git evidence): | 6
Approximate days (reconstructed from file/git timestamps only): | 8
User-reported days (work in a different project folder, not independently verified here): | 1
Notes
- "High" confidence days (Aqua Automation Factory, Aug 21 onward) match an explicit day-by-day work cadence with matching file timestamps and/or git commits, and are the most reliable.
- "Approx." days (Jul 31 - Aug 20, Aqua Automation Factory) are reconstructed from file last-modified timestamps and git commit dates. These are solid evidence that work happened on that date, but since files get edited again later, an early foundational file's timestamp reflects its LAST edit that day, not necessarily everything built that day - so task attribution for this period is best-effort, not a verified log.
- "User-reported" (Aug 10, Self-Healing Tests) was work in a separate project folder not inspected as part of this sheet - included as reported, not independently verified against files/git.
- Gaps between dated entries (e.g. Aug 1-4, Aug 6-9, Aug 11, Aug 15-17, Aug 22-23, Aug 28-30) may include additional work that left no file/commit trace (planning, research, manual testing, or other projects not covered here) - this sheet reflects confirmed evidence, not a complete timesheet.